Visual Search Capstone

Delivery Plan — Requirements and Tasks by Scope

Prepared 2026-08-07   ·   Deadline 2026-09-07   ·   31 days

The headline contribution is engineering: working visual and category-constrained search with measured performance. “Measured” is the load-bearing word — it makes the evaluation set the critical path, not the model.

# Critical path

Two items are calendar-bound rather than effort-bound. Everything else waits on them.

Photograph the query set (PM) — 30–50 phone photos of real catalog products. Cannot be compressed by working harder; must start in week 1 or there is no measured result.

Land a real model (DS-1). Everything semantic is meaningless until the stub is replaced. Blocks all of evaluation and the category constraint.

# Scope 0 — Blocking decisions

Requirement: every question in docs/ds-handoff.md §3 has a written answer before the work it gates begins. Owner DS-1 unless noted.

Confirm final embedding_dim — the column is vector(512); changing it later costs a migration and a full reindex

Answer shared_space — whether image and text vectors live in one space

Choose the model and state its licence explicitly (required for the report)

CPU or GPU — resolved: CPU-only, Hugging Face Spaces free tier

Measure memory ceiling and model load time — drives the cold-start budget

Measure realistic p50/p95 for a one-image request — decides whether the 800 ms budget survives

Confirm optimal batch size — the backend currently assumes 32

Define input constraints, e.g. the minimum resolution below which results are worthless

Decide which of a product's assets to index, and how a multi-image product scores

Decide what text to embed — CLIP's text encoder truncates hard at 77 tokens

Decide where the “no good match” cutoff sits — needs calibration data, not a guess

# Scope 1 — Modelling · DS-1

Requirement: services/embedder returns semantically meaningful 512-d unit vectors for images and text, passes all 20 contract tests, and satisfies every invariant in docs/embedding-service-contract.md.

Implement the five functions in model.py — load_model, preprocess_image, preprocess_text, _embed_image_batch, _embed_text_batch

Pin exact versions in requirements.txt — a numerics-changing upgrade is a REVISION bump

Set MODEL_ID, EMBEDDING_DIM, REVISION, SHARED_SPACE

Keep the EXIF transpose and explicit RGB conversion (already correct in the stub)

Decide crop vs pad and document the choice

Run a warm-up inference inside load_model() so /health returns 503 until genuinely ready

Get the contract tests green before any indexing run

Measure load time, latency and memory — answers decisions 5 and 6

Run the SigLIP comparison on the eval set — roughly two days, no fine-tuning

Out of scope: fine-tuning — no labelled data exists, and no time for a second attempt if the first shows no gain

# Scope 2 — Evaluation · DS-2

Requirement: recall@1 / @5 / @10 against a fixed query set, baseline recorded before any tuning, every later change measured against it, results versioned by embedder revision.

Write the query set spec — 30–50 phone photos of real products, not catalog images

Shoot the photos (with PM) — calendar-bound, start immediately

Label each photo to its ground-truth product

Build the recall@k harness so it reads revision and refuses to mix revisions

Record the baseline on the first real model, before any tuning

Calibrate the “no good match” distance cutoff from the actual distribution

Run ablations — crop vs pad, background handling, constrained vs unconstrained

Produce the CLIP vs SigLIP comparison for the report

Watch for: catalog-against-catalog evaluation flatters the system and hides the domain gap entirely

# Scope 3 — Application: frontend and backend · SWE-1

Requirement: the whole Vendure app — storefront and server — works end to end against the real model.

Already built and verified: plugin, product_asset_embedding entity, vector(512) with HNSW migration, EmbedderService, VisualSearchService, ProductEvent job queue, both Shop API queries, both Admin API operations, 54/54 products indexed. Storefront features/visual-search with drag-drop and mobile camera capture, 4 MB cap, server action, navbar entry, en and km locales.

## Backend

Run a full reindex once the real model lands — a REVISION change makes old rows stale

Build the category constraint — predict the category from the image, then search within it

Add the low-confidence fallback — a wrong guess hides the correct product entirely, so low confidence must not constrain

Pick zero-shot vs kNN majority vote (zero-shot depends on decision 2, shared_space)

Implement hybrid ranking — similarity combined with catalog signals

Enforce the minimum-resolution constraint from decision 8

Confirm batch size against decision 7

Add an Authorization: Bearer header to EmbedderService — not sent today, required by a private Space

## Frontend

Resolve the base64 payload ceiling — a 5 MB photo becomes roughly 6.7 MB of JSON, past Express's default body limit

If fixing it by downscaling client-side, document it as a deliberate choice — it moves preprocessing outside the embedder, the exact index/query drift the contract exists to prevent

Build cold-start UX — a /health 503 means “warming”, not “broken”

Build the “no good match” empty state, wired to the calibrated cutoff from Scope 2

Show what the category constraint narrowed to, and let the user escape it

Polish results for the demo — matched-asset thumbnail, distance display

Keep revision visible until the model is real — the honesty guard on stub results

Regenerate gql.tada types after any Shop API change; the storefront no longer typechecks without the server running

# Scope 4 — Deployment and performance · SWE-2

Requirement: a URL the examiners can open, a demo that survives a cold start, and measured latency against the 800 ms budget. Roughly $10/month, Railway only.

## Deployment

Merge the worker into the server process — a separate service reads an empty volume and writes zero embeddings silently

Deploy pgvector/pgvector:pg16 on Railway — the migration runs CREATE EXTENSION vector

Mount a Railway volume at static/assets — container filesystems are ephemeral

Fix assetUrlPrefix — still the my-shop.com placeholder outside dev

Deploy the embedder to a private Hugging Face Space — sdk: docker and app_port: 8000 in the README frontmatter

Fix the Dockerfile for Spaces — runs as uid 1000, needs a writable HF_HOME, bake weights into a layer

Point embedderUrl at the Space and supply the token

Cron a /health ping — the Space sleeps at 48 h and the wake can exceed the 30 s client timeout

Rehearse the demo from cold

## Performance

Measure end-to-end p50/p95 against the 800 ms budget

Tune HNSW parameters at catalog scale

Measure the cold-start penalty specifically — the number that decides whether warming is sufficient

Load-test the query path

Report back if 800 ms is not reachable — §5 of the handoff says the query path gets redesigned (optimistic UI) rather than the budget quietly slipping

# Scope 5 — Report and submission · PM

Get products photographed — the critical path; blocks all of Scope 2

Write the architecture and boundary chapter (diagrams already exist, reuse them)

State the model licence, from decision 3

Write the results chapter — recall@k, CLIP vs SigLIP, ablations

Write the limitations chapter — domain gap, stub honesty, what was not fine-tuned

Build the slides

Submission dry run on 2026-09-05, leaving two days of buffer

# Biggest risks

Query set not shot in week 1 — no measured result, and the headline contribution collapses. Thirty photos this week beats a perfect fifty in week three.

shared_space turns out false — text search and the zero-shot category route both die; kNN majority vote is the fallback.

Domain gap larger than expected — recall looks fine internally and disappoints on real uploads.

Worker deployed as a separate service — zero embeddings, warnings only, and a clean-looking deploy.

Hugging Face cold start during the demo — 15–40 s of nothing in front of examiners.

Late REVISION change — a full reindex, and every recorded result invalidated. Freeze the model by the end of week 2.

# Notes on the ownership split

SWE-1 is carrying a lot. The whole application in 31 days — category constraint, fallback logic, hybrid ranking, the base64 fix and every piece of UX. SWE-2's deployment work is largely a week-2 burst. Worth deciding now whether SWE-2 picks up hybrid ranking once deployment is stable.

There is a handoff loop. SWE-2 measures what SWE-1 builds, and if the 800 ms budget fails it is SWE-1 who implements the redesign. Performance testing therefore cannot be a week-4 activity — get a first latency number in week 2, while there is still time to act on it.

Two different kinds of performance. SWE-2 measures latency and scale; DS-2 measures recall. Same word, two jobs, two harnesses.